**Second Additional Financing to Ukraine Emergency COVID-19 Response and Vaccination Project**

**ENVIRONMENTAL and SOCIAL**

**COMMITMENT PLAN (ESCP)**

**April 21, 2022**

**ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN**

1. Ukraine, through the Ministry of Health of Ukraine (hereinafter the **Borrower**), shall implement the Ukraine Emergency COVID-19 Response and Vaccination AF Project (the **Project**). The International Bank for Reconstruction and Development(hereinafter the **Bank**) has agreed to provide financing for the Project. The Borrower is currently implementing the parent COVID 19 Response and Vaccination Project (the Parent / Original Project) and its first Additional Financing.
2. The Borrower shall carry out the Project in accordance with the Environmental and Social Standards (**ESSs**). To this end, this Environmental and Social Commitment Plan (**ESCP**) sets out material measures and actions to be carried out or caused to be carried out by the Borrower, including the timeframes of the actions and measures, institutional, staffing, training, monitoring and reporting arrangements, grievance management and the environmental and social assessments and instruments to be prepared or updated, disclosed, consulted, adopted and implemented under the ESCP and the ESSs, all in a manner acceptable to the Bank.
3. Implementation of the material measures and actions set out in this ESCP shall be monitored and reported to the Bank by the Borrower as required by the ESCP and the provisions of the Loan Agreement.
4. As agreed by the Bank and the Borrower, this ESCP may be revised from time to time during Project implementation, to reflect adaptive management of Project changes and unforeseen circumstances or in response to assessment of Project performance conducted under the ESCP itself. In such circumstances, the Borrowershall update the ESCP to reflect the agreed-upon changes. Agreement on changes to the ESCP shall be documented through an exchange of letters signed between the Bank and the Borrower. The Borrower shall promptly disclose the updated ESCP.
5. Where Project changes, unforeseen circumstances, or Project performance result in changes to the risks and impacts during Project implementation, the Borrower shall provide additional funds, if needed, to implement actions and measures to address such risks and impacts.

| **MATERIAL MEASURES AND ACTIONS** | | **TIMEFRAME** | **RESPONSIBLE ENTITY/AUTHORITY** |
| --- | --- | --- | --- |
| **MONITORING AND REPORTING** | | | |
| A | **REGULAR REPORTING**: Prepare and submit to the Bank regular monitoring reports on the environmental, social, health and safety (ESHS) performance of the Project, including but not limited to, stakeholder engagement activities and grievances log. | Quarterly starting from the Effective Date, reports shall be submitted no later than 20 business days after the end of each reporting period, throughout Project implementation | Ministry of Health of Ukraine |
| B | **INCIDENTS AND ACCIDENTS**: Promptly notify the Bank of any incident or accident related to the Project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers (including, inter alia, any COVID outbreak in the Project workforce). Provide sufficient detail regarding the incident or accident, indicating immediate measures taken or that are planned to be taken to address it, and any information provided by any contractor and supervising entity, as appropriate. Subsequently, as per the Bank’s request, prepare a report on the incident or accident and propose any measures to prevent its recurrence. | Notify the Bank within 48 hours after learning of the incident or accident. Subsequent report shall be provided within a timeframe acceptable to the Bank, as requested. | Ministry of Health of Ukraine |
| **ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS** | | | |
| 1.1 | **ORGANIZATIONAL STRUCTURE**: The Ministry of Health of Ukraine shall establish and maintain a PIU with qualified staff and resources to support management of ESHS risks and impacts of the Project, including an environmental and social specialist. PIU's capacity to support the national vaccination implementation campaign will be strengthened by hiring additional consultants to work alongside the environmental and social specialist as needed. | The PIU has two environmental and social focal points, and waste management specialist. Third-party monitoring and Bank monitoring of ES performance will be regularly assessed to determine the need for additional consultants (e.g. OHS specialist).  PIU shall be maintained throughout Project implementation. | Ministry of Health of Ukraine |
| 1.2 | **ENVIRONMENTAL AND SOCIAL ASSESSMENT/MANAGEMENT PLANS AND INSTRUMENTS/ CONTRACTORS**   1. The Environmental and Social Management Framework (ESMF) for the parent project to be updated (including ICWMP update), disclosed, consulted upon and adopted for the AF Project. The ESMF will comply with the ESSs, the Environmental, Health and Safety Guidelines (EHSGs), and other relevant Good International Industry Practice (GIIP), including relevantWHO guidelines. 2. Prepare, disclose, consult upon, adopt and implement any Environmental and Social Management Plans (e.g. Infection Control and Waste Management Plans), instruments or other measures required for the respective Project activities based on the assessment process, in accordance with the ESSs, the ESMF, the EHSGs, and other relevant Good International Industry Practice (GIIP), including relevant WHO guidelinesto, inter alia, ensure access to and allocation of Project benefits in a fair, equitable and inclusive manner, taking into account the needs of individuals or groups who, because of their particular circumstances, may be disadvantaged or vulnerable (including, as relevant, with regards to vaccines) 3. Conduct environmental and social assessment of vaccine distribution, cold chain and waste management aspects 4. Incorporate the relevant aspects of this ESCP, including, inter alia, the ESMF, any environmental and social management plans or other instruments, ESS2 requirements, and any other required ESHS measures, into the ESHS specifications of the procurement documents and contracts with contractors and supervising firms. Thereafter ensure that the contractors and supervising firms comply with the ESHS specifications of their respective contracts 5. Adopt procedures, protocols and/or other measures related to vaccine delivery to follow a prioritized program that targets (at least initially) front line workers, vulnerable people, etc. 6. Adopt procedures, protocols and/or other measures to ensure Project beneficiaries that receive vaccines under the Project do so under a program that does not include forced vaccination and is acceptable to the Bank, as set out in the ESMF. | 1. The prepared original project’s ESMF (including ICWMP) was updated to include activities covered by the AF, disclosed at the project website, however will beconsulted upon,and redisclosed at official MoH website and adopted once the situation in country allows. ESMF shall be further updated throughout Project implementation if required. 2. Plans/instruments shall be prepared, disclosed, consulted upon and adopted before the carrying out of the relevant Project activities, and thereafter implemented throughout the carrying out of such activities 3. By the end of the Project 4. The relevant ESHS measures shall be incorporated into the procurement documents before launching the procurement process for the relevant Project activities, and shall thereafter complied with throughout the carrying out of such activities 5. Before the carrying out of the relevant Project activities, and thereafter implemented throughout the carrying out of such activities 6. Before the carrying out of the relevant Project activities, and thereafter implemented throughout the carrying out of such activities. | Ministry of Health of Ukraine |
| 1.3 | **EXCLUSIONS:** Exclude the following types of activities as ineligible for financing under the Project:   * Civil works*.* * Activities that may cause physical or economic displacement*.* * Activities that involve forced or child labor. * All the other excluded activities set out in the ESMF of the Project*.* | During the assessment process conducted under action 1.2.a. above. | Ministry of Health of Ukraine |
|  |  |  |  |
| **ESS 2: LABOR AND WORKING CONDITIONS** | | | |
| 2.1 | **LABOR MANAGEMENT:** The Project shall be carried out in accordance with the applicable requirements of ESS2 including through, inter alia, implementing adequate occupational health and safety measures (including personal protective equipment, and emergency preparedness and response measures), setting out grievance mechanisms for Project workers, and incorporating labor requirements into the ESHS specifications of the procurement documents and contracts with contractors and supervising firms | The LMP as part of the ESMF was updated and disclosed at the project official website. However it will be consulted upon, redisclosed at the official MoH website and adopted once the situation allows. It shall thereafter be implemented throughout the life of the Project. The LMP as part of the ESMF shall be further updated throughout Project implementation if required. | Ministry of Health of Ukraine |
| **ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT** | | | |
| 3.1 | Conduct in-depth country-wide waste management system needs assessment covering waste management capacity (including information on waste management facilities of health/medical waste in Ukraine existing service providers, the waste transportation and disposal facilities, licensing, operational practices, and performance) and waste management needs of the vaccination/testing campaign | The waste management system needs assessment will be prepared no later than 30 days after the Effective Date | Ministry of Health of Ukraine |
| 3.2 | Following waste management system needs assessment, develop distribution list for the equipment to neutralize medical waste from COVID-19 | The distribution list for the equipment to neutralize medical waste will be prepared no later than 60 days after the Effective Date | Ministry of Health of Ukraine |
| 3.3 | Relevant aspects of this standard shall be considered, as needed, under action 1.2 above, including, inter alia, measures reflected in the ICWMP to: carry out the purchase*,* storage, transportation and handling of vaccines (including, cold chain management) in a safe manner and in accordance with the EHSGs, and other relevant GIIP including relevant WHO guidelines; and adequately manage and dispose of health care wastes (including, vaccines and other types of hazardous and non-hazardous wastes). | Throughout Project implementation. | Ministry of Health of Ukraine |
| **ESS 4: COMMUNITY HEALTH AND SAFETY** | | | |
| 4.1 | **COMMUNITY HEALTH AND SAFETY:**  Relevant aspects of this standard shall be considered, as needed, under action 1.2 above including, inter alia, measures to: minimize the potential for community exposure to communicable diseases; establish and implement appropriate quality management systems to manage the risks and the impacts that services provided and activities carried out under the Project may have on community health and safety; manage the risks of the use of security personnel; manage the risks of labor influx; and prevent and respond to sexual exploitation and abuse, and sexual harassment and violence against children. | Throughout Project implementation. | Ministry of Health of Ukraine |
| 4.2 | **USE OF SECURITY PERSONNEL:**  In case the Borrower’s military or security forces (“security personnel”) are used in the implementation of Project activities and/or for provision of security to Project workers, sites and/or assets, the MOH shall, in coordination with other government authorities, as relevant, implement the following measures:  a) Assess the risks and impacts of involving security personnel and implement measures to manage such risks and impacts, as described in action 1.2 above, guided by the principles of proportionality and GIIP, and by applicable law, in relation to hiring, rules of conduct, training, equipping, and monitoring of such personnel;  b) Ensure that stakeholder engagement activities under the Stakeholder Engagement Plan (SEP) include a communication strategy on the involvement of security personnel under the Project;  c) Ensure that any concerns or grievances regarding the conduct of security personnel are received, monitored, documented (protecting the confidentiality),resolved through the Project’s grievance mechanism (see action 10.2 below) and reported to the Bank no later than 5 days after being received;  d) Ensure that (i) standards, protocols and codes of conduct are followed for the selection and use of security personnel, and screen such personnel to verify that they have not been engaged in past unlawful or abusive behavior, including SEA, SH or excessive use of force; and (ii) that such personnel is adequately instructed and trained, on a regular basis, on the use of force and appropriate behavior and conduct (including in relation to SEA and SH), as set out in the ESMF. | a) Assessment carried out in the same timeframe than action 1.2 a) above and any required measures shall be adopted before deploying security personnel under the Project and thereafter implemented throughout Project implementation.  b) and c) As set out under actions 10.1 and 10.2 respectively.  d) Before deploying security personnel under the Project and thereafter throughout Project implementation. | Ministry of Health of Ukraine |
| **ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT** | | | |
|  | Not relevant | Throughout Project implementation. | Ministry of Health of Ukraine |
| **ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES** | | | |
|  | Not relevant | Throughout Project implementation. | Ministry of Health of Ukraine |
| **ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES** | | | |
| 7.1 | Not relevant | Throughout Project implementation. | Ministry of Health of Ukraine |
| **ESS 8: CULTURAL HERITAGE** | | | |
|  | Not relevant | Throughout Project implementation. | Ministry of Health of Ukraine |
| **ESS 9: FINANCIAL INTERMEDIARIES** | | | |
|  | Not relevant | Throughout Project implementation. | Ministry of Health of Ukraine |
| **ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE** | | | |
| 10.1 | **STAKEHOLDER ENGAGEMENT PLAN:** Revise, disclose, consult, adopt and implement a Stakeholder Engagement Plan (SEP) for the AF consistent with ESS10, which shall include measures to, inter alia, provide stakeholders with timely, relevant, understandable and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation. | A revised draft of the Parent Project SEP that will cover AF activities has been prepared and disclosed at the project official website. and shall be consulted, updated, redisclosed at the official MoH website and adopted once the situation in country allows. The updated SEP including AF activities shall be implemented throughout Project implementation. | Ministry of Health of Ukraine |
| 10.2 | **GRIEVANCE MECHANISM:** An accessible grievance mechanism shall be established, publicized, maintained and operated to receive and facilitate resolution of concerns and grievances in relation to the Project, promptly and effectively, in a transparent manner that is culturally appropriate and readily accessible to all Project-affected parties, at no cost and without retribution, including concerns and grievances filed anonymously, in a manner consistent with ESS10.  The grievance mechanism shall also receive, register and address concerns and grievances related to the sexual exploitation and abuse, sexual harassment in a safe and confidential manner that reflects a survivor-center approach, including the referral of survivors to gender-based violence service providers.  The grievance mechanism shall also receive, register and address/refer respectively concerns arising from unintended health consequences after vaccination especially those resulting in serious adverse effects. | The GRM was established under the Parent Project and shall be maintained throughout AF Project implementation. | Ministry of Health of Ukraine |
| **CAPACITY SUPPORT (TRAINING)** | | | |
| CS1 | Project Implementation Unit and other relevant implementing support staff responsible for the Project to receive training on the Project’s ESHS plans and instruments, fair, equitable and inclusive access and allocation of Project benefits (including with regards to vaccines), and the roles and responsibilities of different key agencies in the ESF implementation. | No later than 60 days after the Effective Date and periodically with the addition of new Project team members join the Project throughout implementation. | Ministry of Health of Ukraine |